## Capacity
Monthly Capacity per resource
| Monthly Available Capacity-Hours | [11 empty] | Vacation/Off - No of Days
| 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2015-01-14 | 2015-02-14 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01
Arpit Gupta | 168 | 160 | 160 | 160 | 152 | 160 | 176 | 160 | 168 | 168 | 160 | 176 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Satyam Tripathi | 168 | 160 | 120 | 160 | 152 | 160 | 176 | 160 | 168 | 168 | 160 | 176 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Akash Deep | 168 | 160 | 160 | 96 | 152 | 160 | 176 | 160 | 168 | 168 | 160 | 176 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Madan | 168 | 160 | 160 | 160 | 152 | 160 | 176 | 160 | 168 | 168 | 160 | 176 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total | 672 | 640 | 600 | 576 | 608 | 640 | 704 | 640 | 672 | 672 | 640 | 704
Number of work days(After removing public holidays and weekly off) | 22 | 21 | 21 | 21 | 20 | 21 | 23 | 21 | 22 | 22 | 21 | 23
Productive hours | 8
Monthly % Task Allocation
| 2015-01-01 |  | 2015-02-01 |  | 2015-03-01 |  | 2015-04-01 |  | 2015-05-01 |  | 2015-06-01 |  | 2015-07-01 |  | 2015-08-01 |  | 2015-09-01 |  | 2015-10-01 |  | 2015-11-01 |  | 2015-12-01
| New s/w | Old S/W | New s/w | Old S/W | New S/w | Old S/W | New Sw | Old S/W | New S/w | Old S/W | New S/w | Old S/W | New s/w | Old S/W | New s/w | Old S/W | New S/w | Old S/W | New S/w | Old S/W | New S/w | Old S/W | New S/w | Old S/W
Arpit Gupta (Devlopment + Leadership) | 50% | 50% | 50% | 50% | 50% | 50% | 30% | 70% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
Satyam Tripathi [Old S/W maintanance and enhancement] | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100%
Akash Deep [New s/w development] | 100% | 0% | 100% | 0% | 100% | 0% | 50% | 50% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0%
Madan [New s/w development] | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 0%
Available monthly capacity
| 2015-01-01 |  | 2015-02-01 |  | 2015-03-01 |  | 2015-04-01 |  | 2015-05-01 |  | 2015-06-01 |  | 2015-07-01 |  | 2015-08-01 |  | 2015-09-01 |  | 2015-10-01 |  | 2015-11-01 |  | 2015-12-01
| New s/w | Old S/W | New s/w | Old S/W | New Sw | Old S/W | New Sw | Old S/W | New Sw | Old S/W | New Sw | Old S/W | New s/w | Old S/W | New s/w | Old S/W | New Sw | Old S/W | New Sw | Old S/W | New Sw | Old S/W | New Sw | Old S/W
Arpit Gupta (Devlopment + Leadership) | 10.5 | 10.5 | 10 | 10 | 10 | 10 | 6 | 14 | 9.5 | 9.5 | 10 | 10 | 11 | 11 | 10 | 10 | 10.5 | 10.5 | 10.5 | 10.5 | 10 | 10 | 11 | 11
Satyam Tripathi [Old S/W maintanance and enhancement] | 0 | 21 | 0 | 20 | 0 | 15 | 0 | 20 | 0 | 19 | 0 | 20 | 0 | 22 | 0 | 20 | 0 | 21 | 0 | 21 | 0 | 20 | 0 | 22
Akash Deep [New s/w development] | 21 | 0 | 20 | 0 | 20 | 0 | 6 | 6 | 19 | 0 | 20 | 0 | 22 | 0 | 20 | 0 | 21 | 0 | 21 | 0 | 20 | 0 | 22 | 0
Madan [New s/w development] | 21 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 19 | 0 | 20 | 0 | 22 | 0 | 20 | 0 | 21 | 0 | 21 | 0 | 20 | 0 | 22 | 0
Total | 52.5 | 31.5 | 50 | 30 | 50 | 25 | 32 | 40 | 47.5 | 28.5 | 50 | 30 | 55 | 33 | 50 | 30 | 52.5 | 31.5 | 52.5 | 31.5 | 50 | 30 | 55 | 33
Number of days in plan for new s/w | 597
Project Start Date | 2014-12-15
Estimated Completion Date
Modules | Total Task Days | Completed % | Pending Work Days
Masters | 86 | 80 | 17.5
Sales | 93 | 60 | 37.5
Planning | 57 | 44 | 30
Purchase | 76.5 | 29 | 50.625
Weaving | 94 | 0 | 94
Dyeing | 67 | 0 | 67
Trace Map | 27 | 0 | 27
Finishing | 76.5 | 0 | 76.5
Inventory | 42 | 0 | 42
Total | 619 |  | 442.125

## Master Pages
| Master Pages | [5 empty] | Delay Reasons
| Resouces | 2.5 | Task Completed % | 80
| Task Days | 86 | Pending Task Days | 17.5
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Carpet Master | Design Master |  | 5 | 100% | 0
2 | Carpet Master | Colour Ways |  | 0.25 | 100% | 0
3 | Carpet Master | Collection |  | 0.25 | 100% | 0
4 | Carpet Master | Construction |  | 0.25 | 100% | 0
5 | Carpet Master | Quality |  | 0.25 | 100% | 0
6 | Carpet Master | Size |  | 1 | 100% | 0
7 | Carpet Master | Size Type | Standard, Manufacturing, Finishing | 0.25 | 100% | 0
8 | Carpet Master | Shape |  | 0.25 | 100% | 0
9 | Carpet Master | Content |  | 1 | 100% | 0
10 | Carpet Master | Design Consumption |  | 1 | 100% | 0
11 | Carpet Master | Process Sequence |  | 1 | 100% | 0
12 | Carpet Master | Colour |  | 0.25 | 100% | 0
13 | Carpet Master | Style |  | 0.25 | 100% | 0
14 | Carpet Master | Pattern |  | 0.25 | 100% | 0
17 | Carpet Master | Designer |  | 1 | 100% | 0
15 | Product Master | Invoice Group |  | 0.25 | 100% | 0
16 | Product Master | Drawback Tariff |  | 0.25 | 100% | 0
18 | Product Master | Product Nature |  | 0.25 | 100% | 0
19 | Product Master | Product Type |  | 0.25 | 100% | 0
20 | Product Master | Finished Product |  | 3 | 100% | 0
21 | Product Master | Product Group |  | 0.25 | 100% | 0
22 | Product Master | Product Category |  | 0.25 | 100% | 0
23 | Product Master | Product Consumption |  | 2 | 100% | 0
24 | Person Master | Unit |  | 0.5 | 100% | 0
25 | Person Master | City |  | 0.5 | 100% | 0
26 | Person Master | State |  | 0.25 | 100% | 0
27 | Person Master | Country |  | 0.25 | 100% | 0
28 | Inventory Masters | Godown |  | 0.25 | 100% | 0
29 | Product Master | Product Custom Group |  | 1 | 100% | 0
30 | Person Master | Person Rate Group |  | 0.25 | 100% | 0
31 | Person Master | Customer |  | 2 | 100% | 0
32 | Person Master | Supplier |  | 0.5 | 100% | 0
33 | Person Master | Employee |  | 1 | 100% | 0
34 | Production | Process |  | 2 | 100% | 0
35 | Accounts Master | Cost Center |  | 0.5 | 100% | 0
36 | Person Master | Job Worker |  | 0.25 | 100% | 0
37 | Person Master | Department |  | 0.25 | 100% | 0
38 | Person Master | Designation |  | 0.25 | 100% | 0
39 | Company Masters | Division |  | 0.25 | 100% | 0
40 | Company Masters | Site |  | 0.25 | 100% | 0
41 | Accounts Master | Ledger Account |  | 0.5 | 100% | 0
42 | Accounts Master | Ledger Account Group |  | 0.5 | 100% | 0
43 | Inventory Masters | Raw Material Master |  | 1 | 100% | 0
44 | Inventory Masters | Other Material Master |  | 1 | 100% | 0
45 | Person Master | Agent |  | 1 | 100% | 0
49 | Purchase/Sales | Delivery Terms |  | 0.25 | 100% | 0
50 | Purchase/Sales | Ship Method |  | 0.25 | 100% | 0
51 | General Masters | Reason |  | 0.25 | 100% | 0
52 | Person Master | Person Contact Type |  | 0.25 | 100% | 0
53 | Purchase/Sales | Sales Tax Product Group |  | 0.25 | 100% | 0
54 | Purchase/Sales | Sales Tax Party Group |  | 0.25 | 100% | 0
55 | General Masters | Document Type |  | 0.25 | 100% | 0
56 | General Masters | Document Category |  | 0.25 | 100% | 0
57 | Accounts Master | TDS Category |  | 0.25 | 100% | 0
58 | Accounts Master | TDS Group |  | 0.25 | 100% | 0
59 | Accounts Master | Currency |  | 1 | 100% | 0
60 | Product Master | Product Type Attribute |  | 1 | 100% | 0
60 | Product Master | Stencil |  | 1.5 | 50% | 0.75
60 | Product Master | Map |  | 1.5 | 50% | 0.75
60 | Calculation | Charges |  | 0.5 | 100% | 0
60 | Calculation | ChargesGroupPerson |  | 0.5 | 100% | 0
60 | Calculation | ChargesGroupProduct |  | 0.5 | 100% | 0
| Testing & Fixing |  |  | 9 | 100% | 0
| Data Migration | Data Migration from old to new | Trriggers for new to old | 15 | 100% | 0
| UAT, Fixing, Implementation |  |  | 20 | 20% | 16
End

## Sales
| Sales Pages | [5 empty] | Delay Reasons
| Resouces | 2.5 | Task Completed % | 60
| Total Task Days | 93 | Pending Task Days | 37.5
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Transactions | Sales Order | Covers the input of sales order data, approval of | 5 | 100% | 0
| Transactions | Sales Order Cancel | Discontinue product. Some times some pcs are not required in PO after a week or later. | 3 | 100% | 0
|  | Sales Order Amendment | Some times some more sku are added in PO after a week or later | 4 | 100% | 0
2 | Transactions | Packing | Buyer wise packing, stock to be checked, by default deducted from oldest sales order, image of design should be displayed at the time of packing | 6 | 100% | 0
3 | Transactions | Invoice | Sales Invoice through packing | 5 | 100% | 0
4 | Transactions | Shipment Data | Concor Booking No, Weight, Freight etc. | 3 | 100% | 0
3 | Transactions | After Shipment Data Update | Released from madhosingh, reached at kanpur, released from kanpur, reached at mumbai, released from mumbai, Shipping Line, B/L date etc. | 3 | 75% | 0.75
4 | Reports | Sales Order Document Print |  | 1 | 100% | 0
5 | Reports | Export Documents | Invoice, Packing List, Single Country Declaration etc. | 10 | 100% | 0
| Reports | Sales Order Report | Header detail, Product wise detail | 1 | 75% | 0.25
| Reports | Sales Order Cancel Report | Header detail, Product wise detail | 1 | 75% | 0.25
| Reports | Sales Order Summary Report | Design Wise, Construction Wise, Collection Wise etc | 2 | 75% | 0.5
| Reports | Sales Order Status | Sale Order, Product Wise Status and Detail | 3 | 75% | 0.75
| Reports | Sales Order Balance | Sale Order, Product Wise Status and Detail | 2 | 75% | 0.5
| Reports | Sales Order Status Summary | Design Wise, Construction Wise, Collection Wise etc | 2 | 75% | 0.5
| Reports | Packing Report | Daily Packing, User wise packing | 3 | 0% | 3
| Reports | Sales Invoice Report | Header detail, Product wise detail | 2 | 75% | 0.5
| Reports | Sales Invoice Summary | Design Wise, Construction Wise, Collection Wise etc | 2 | 75% | 0.5
| Testing & Fixing |  |  | 10 | 50% | 5
| Data Migration | Data Migration from old to new | Trriggers for new to old | 10 | 0% | 10
| UAT, Fixing, Implementation |  |  | 15 | 0% | 15
End

## Planning
| Planning Pages | [5 empty] | Delay Reasons
| Total Task Days | 57 | Pending Task Days | 30
| Resouces | 2.5 | Task Completed % | 44
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Transactions | Sale Order Planning |  | 3 | 100% | 0
1 | Transactions | Dyed Yarn Planning |  | 5 | 100% | 0
| Transactions | Undyed Yarn Planning |  | 3 | 100% | 0
| Transactions | Trace Map Planning |  | 3 | 0% | 3
| Transactions | Material Planning |  | 3 | 90% | 0.3
| Transactions | Production Order |  | 3 | 90% | 0.3
| Transactions | Production Order Cancel |  | 3 | 90% | 0.3
| Report | Planning Status Reports |  | 10 | 0% | 10
| Testing & Fixing |  |  | 7 | 70% | 2.1
| Data Migration | Data Migration from old to new | Trriggers for new to old | 7 | 0% | 7
| UAT, Fixing, Implementation |  |  | 10 | 30% | 7
End

## Purchase
| Purchase Pages | [5 empty] | Delay Reasons
| Total Task Days | 76.5 | Pending Task Days | 50.625
| Resouces | 2.5 | Task Completed % | 29
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Transactions | Purchase Indent |  | 3 | 90% | 0.3
| Transactions | Purchase Indent Cancel |  | 3 | 90% | 0.3
1 | Transactions | Purchase Order |  | 5 | 90% | 0.5
| Transactions | Purchase Order Cancel |  | 3 | 90% | 0.3
| Transactions | Purchase Waybill |  | 3 | 90% | 0.3
2 | Transactions | Goods Receive |  | 3 | 90% | 0.3
2 | Transactions | Goods Return |  | 3 | 0% | 3
3 | Transactions | Purchase Invoice |  | 5 | 0% | 5
| Reports | Purchase Indent Report | Product wise detail | 1 | 75% | 0.25
| Reports | Purchase Indent Status |  | 1 | 75% | 0.25
| Reports | Purchase Indent Status Detail |  | 1 | 75% | 0.25
| Reports | Purchase Indent Balance |  | 1 | 0% | 1
| Reports | Purchase Order Report | Header detail, Product wise detail | 1 | 75% | 0.25
| Reports | Purchase Order Cancel Report | Header detail, Product wise detail | 1 | 75% | 0.25
| Reports | Purchase Order Summary |  | 1.5 | 75% | 0.375
| Reports | Purchase Order Status |  | 2 | 75% | 0.5
| Reports | Purchase Order Status Summary |  | 2 | 0% | 2
| Reports | Purchase Order Balance |  | 1 | 75% | 0.25
| Reports | Purchase Challan Report |  | 1 | 0% | 1
| Reports | Purchase invoice Report |  | 1 | 75% | 0.25
| Testing & Fixing |  |  | 9 | 0% | 9
| Data Migration | Data Migration from old to new | Trriggers for new to old | 10 | 0% | 10
| UAT, Fixing, Implementation |  |  | 15 | 0% | 15
End

## Weaving
| Weaving Pages | [5 empty] | Delay Reasons
| Total Task Days | 94 | Pending Task Days | 94
| Resouces | 2.5 | Task Completed % | 0
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Transactions | Weaving Order | Weaved Carpet, Finished Carpet, Product Against Production Order, Extra Order | 8 | 0% | 8
| Transactions | Weaving Order Cancel |  | 5 | 0% | 5
| Transactions | Material Issue for Job Work |  | 3 | 0% | 3
1 | Transactions | Material Return from Job Work |  | 3 | 0% | 3
| Transactions | Material Exchange for Job Work |  | 3 | 0% | 3
| Transactions | Material Not Needed for Job Work |  | 3 | 0% | 3
| Transactions | Weaving Bazar |  | 5 | 0% | 5
| Transactions | Weaving Payment Entry |  | 3 | 0% | 3
1 | Transactions | Weaving TDS Entry |  | 3 | 0% | 3
| Transactions | Retention Payment Entry |  | 5 | 0% | 5
| Transactions | Weaving Cheque Cancel Entry |  | 3 | 0% | 3
1 | Transactions | Material Transfer Between Weaving Orders |  | 3 | 0% | 3
| Transactions | Amount Transfter Between Weaving Orders |  | 3 | 0% | 3
| Transactions | Material Rate Sattlement |  | 3 | 0% | 3
| Transactions | Material Consumption Adjustment |  | 3 | 0% | 3
| Transactions | Debit Note Entry |  | 3 | 0% | 3
| Transactions | Credit Note Entry |  | 3 | 0% | 3
| Transactions | Time Incentive |  | 2 | 0% | 2
| Transactions | Time Penalty |  | 3 | 0% | 3
| Transactions | Segmentation Penalty |  | 3 | 0% | 3
| Transactions | Bulk Bazar Scheme Master |  | 3 | 0% | 3
| Transactions | Bulk Bazar Scheme |  | 3 | 0% | 3
| Transactions | Money Receipt |  | 2 | 0% | 2
| Standard Reports | Weaving Order Report | Header detail, Product wise detail | 1 | 0% | 1
2 | Standard Reports | Weaving Order Cancel | Product wise detail | 1 | 0% | 1
2 | Standard Reports | Material Issue For Weaving Report | Header detail, Product wise detail | 1 | 0% | 1
3 | Standard Reports | Material Return From Weaving Report | Header detail, Product wise detail | 1 | 0% | 1
| Standard Reports | Material Exchange Report | Header detail, Product wise detail | 1 | 0% | 1
| Standard Reports | Material Not Needed Report | Header detail, Product wise detail | 1 | 0% | 1
| Standard Reports | Weaving Bazar Report | Header detail, Product wise detail | 1 | 0% | 1
| Standard Reports | Weaving Payment Report | Jobworker wise detail | 1 | 0% | 1
| Standard Reports | Weaving TDS Report | Jobworker wise detail | 1 | 0% | 1
| Standard Reports | Weaving Retention Payment Report | Jobworker wise detail | 1 | 0% | 1
| Standard Reports | Weaving Cheque Cancel Report | Cheque / Jobworker wise detail | 1 | 0% | 1
| Standard Reports | Material Trf. between weaving order report |  | 1 | 0% | 1
| Standard Reports | Amount Trf. Between weaving order report |  | 1 | 0% | 1
| Standard Reports | Weaving material rate settlement report |  | 1 | 0% | 1
| Standard Reports | Weaving consumption adjustment report |  | 1 | 0% | 1
| Standard Reports | Debit note report |  | 1 | 0% | 1
| Standard Reports | Credit note report |  | 1 | 0% | 1
| Standard Reports | Time Incentive Report |  | 1 | 0% | 1
| Standard Reports | Time Penalty Report |  | 1 | 0% | 1
| Standard Reports | Scheme Incentive Report |  | 1 | 0% | 1
| Summary Reports | Weaving Payment Summary |  | 1 | 0% | 1
| Summary Reports | Weaving Payment Advice |  | 2 | 0% | 2
| Summary Reports | Weaving Production Summary |  | 2 | 0% | 2
| Summary Reports | Balance Order From Loom |  | 2 | 0% | 2
| Summary Reports | Weaving Order Position |  | 2 | 0% | 2
| Summary Reports | Material Issue Against Order |  | 2 | 0% | 2
| Summary Reports | Contractor Outstanding Report |  | 2 | 0% | 2
| Summary Reports | Working Status |  | 2 | 0% | 2
| Summary Reports | Weaving Register |  | 2 | 0% | 2
| Summary Reports | Weaving Payable Ledger |  | 2 | 0% | 2
| Summary Reports | Actual Lagat Design wise summary |  | 2 | 0% | 2
| Summary Reports | List of Purja |  | 2 | 0% | 2
| Summary Reports | Hisab Of Purja |  | 2 | 0% | 2
| Summary Reports | Material On Loom |  | 2 | 0% | 2
| Summary Reports | Contractor Status |  | 2 | 0% | 2
| Summary Reports | To Be Issue Dyeing Status |  | 2 | 0% | 2
| Summary Reports | Weaving Order Stock Status |  | 2 | 0% | 2
| Summary Reports | Bazar wise Weaving Consumption |  | 2 | 0% | 2
| Summary Reports | Weaving Consumption Comparison |  | 2 | 0% | 2
End

## Dyeing
| Purchase Pages | [5 empty] | Delay Reasons
| Total Task Days | 67 | Pending Task Days | 67
| Resouces | 2.5 | Task Completed % | 0
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Transactions | Dyeing Order | Washing, Latexing, Pattimurai, Thirdbacking, Binding etc. | 5 | 0% | 5
1 | Transactions | Dyeing Order Cancel |  | 3 | 0% | 3
1 | Transactions | Dyeing Order Rate Amendment |  | 3 | 0% | 3
1 | Transactions | Material Issued for Dyeing |  | 3 | 0% | 3
1 | Transactions | Material Returned from Dyeing |  | 3 | 0% | 3
| Transactions | Dyeing Receive |  | 4 | 0% | 4
| Transactions | Dyeing Return |  | 3 | 0% | 3
1 | Transactions | Dyeing Invoice |  | 4 | 0% | 4
2 | Transactions | Material Rate Settlement |  | 4 | 0% | 4
2 | Transactions | Consumption Adjustment |  | 3 | 0% | 3
3 | Transactions | Debit Note |  | 2 | 0% | 2
| Transactions | Credit Note |  | 2 | 0% | 2
| Reports | Dyeing Order Report | Header detail, Product wise detail | 1 | 0% | 1
| Reports | Dyeing Order Cancel Report | Header detail, Product wise detail | 1 | 0% | 1
| Reports | Dyeing Order Amendment Report | Header detail, Product wise detail | 1 | 0% | 1
| Reports | Material Issued for Dyeing Report | Header detail, Product wise detail | 1 | 0% | 1
| Reports | Material Returned from Dyeing Report |  | 1 | 0% | 1
| Reports | Dyeing Receive Report |  | 1 | 0% | 1
| Reports | Dyeing Return Report |  | 2 | 0% | 2
| Reports | Dyeing Invoice Report |  | 1 | 0% | 1
| Reports | Dyeing Order Status Report |  | 3 | 0% | 3
| Reports | Dyeing Order Balance Report |  | 2 | 0% | 2
| Reports | Dyeing Status Summary Periodic |  | 2 | 0% | 2
| Reports | Shade Movement Report |  | 2 | 0% | 2
| Reports | Dyeing Analysis Report |  | 3 | 0% | 3
| Testing & Fixing |  |  | 7 | 0% | 7
End

## Trace Map
| Purchase Pages | [5 empty] | Delay Reasons
| Total Task Days | 27 | Pending Task Days | 27
| Resouces | 2.5 | Task Completed % | 0
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Transactions | Trace Map Order |  | 3 | 0% | 3
| Transactions | Trace Map Receive |  | 3 | 0% | 3
1 | Transactions | Trace Map Invoice |  | 3 | 0% | 3
| Transactions | Trace Map Issue to Jobworker |  | 3 | 0% | 3
2 | Transactions | Trace Map Receive from Jobworker |  | 3 | 0% | 3
2 | Transactions | Trace Map Write off |  | 3 | 0% | 3
| Reports | Trace Map Order Report |  | 1 | 0% | 1
| Reports | Trace Map Receive Report |  | 1 | 0% | 1
| Reports | Trace Map Invoice Report |  | 1 | 0% | 1
| Reports | Trace Map Order Status Report |  | 1 | 0% | 1
| Reports | Trace Map Order Balance Report |  | 1 | 0% | 1
| Reports | Trace Map Balance at jobworker |  | 1 | 0% | 1
| Testing & Fixing |  |  | 3 | 0% | 3
End

## Finishing
| Purchase Pages | [5 empty] | Delay Reasons
| Total Task Days | 76.5 | Pending Task Days | 76.5
| Resouces | 2.5 | Task Completed % | 0
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Transactions | Finishing Order | Washing, Latexing, Pattimurai, Thirdbacking, Binding etc. | 10 | 0% | 10
1 | Transactions | Finishing Order Cancel |  | 5 | 0% | 5
1 | Transactions | Finishing Order Rate Amendment |  | 6 | 0% | 6
| Transactions | Material Issued for finishing |  | 3 | 0% | 3
| Transactions | Finishing Receive |  | 5 | 0% | 5
1 | Transactions | Finishing Invoice |  | 6 | 0% | 6
| Transactions | Finishing Invoice Amendment |  | 6 | 0% | 6
2 | Transactions | Finishing Payment |  | 3 | 0% | 3
2 | Transactions | Finishing TDS |  | 3 | 0% | 3
3 | Transactions | Debit Note |  | 2 | 0% | 2
| Transactions | Credit Note |  | 2 | 0% | 2
| Reports | Finishing Order Report | Header detail, Product wise detail | 1 | 0% | 1
| Reports | Finishing Order Cancel Report | Header detail, Product wise detail | 1 | 0% | 1
| Reports | Finishing Order Amendment Report | Header detail, Product wise detail | 1 | 0% | 1
| Reports | Finishing Receive Report | Header detail, Product wise detail | 1 | 0% | 1
| Reports | Finishing Invoice Report |  | 1.5 | 0% | 1.5
| Reports | Finishing Order Status Report |  | 3 | 0% | 3
| Reports | Finishing Order Balance Report |  | 2 | 0% | 2
| Reports | Finishing Order Status Summary Periodic |  | 3 | 0% | 3
| Reports | Material Issue for Finishing Report |  | 1 | 0% | 1
| Reports | Actual Payment Advice |  | 2 | 0% | 2
| Testing & Fixing |  |  | 9 | 0% | 9
End

## Inventory
| Purchase Pages | [5 empty] | Delay Reasons
| Total Task Days | 42 | Pending Task Days | 42
| Resouces | 2.5 | Task Completed % | 0
Sr | Module | Sub Module | Description | Man Days | Progress | Pending | Comments
1 | Transactions | Material Request |  | 3 | 0% | 3
| Transactions | Material Issue |  | 3 | 0% | 3
1 | Transactions | Material Receive |  | 3 | 0% | 3
| Transactions | Material Transfer |  | 3 | 0% | 3
2 | Transactions | Internal Process |  | 3 | 0% | 3
2 | Transactions | Gatepass |  | 3 | 0% | 3
3 | Transactions | Stock Reconciliation |  | 5 | 0% | 5
| Reports | Material Request Report |  | 1 | 0% | 1
| Reports | Material Request Status |  | 1 | 0% | 1
| Reports | Material Issue Report |  | 1 | 0% | 1
| Reports | Material Receive Report |  | 1 | 0% | 1
| Reports | Material Transfer Report |  | 1 | 0% | 1
| Reports | Stock In Hand |  | 1 | 0% | 1
| Reports | Stock Summary |  | 3 | 0% | 3
| Reports | Stock Ledger |  | 2 | 0% | 2
| Reports | Stock Valuation (FIFO) |  | 3 | 0% | 3
| Testing & Fixing |  |  | 5 | 0% | 5
End